## Product Backlog
Use Cases | Time Estimate | Sprint Assigned
See map broken up by DEC regions | 3 | 1
Save Game | 6
Create store to spend money in | 3 | 1
Create difficulty options | 5
Create color blind settings in options | 4
Create volume settings in options | 3
Have realistic options in the store to slow the spread | 5
Create a tutorial | 6
Create a start screen | 3 | 1
Create an end screen | 3 | 1

## Sprint 1
| 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18
Actual Trend | 12 | 11.0769 | 10.1538 | 9.2308 | 8.3077 | 7.3846 | 6.4615 | 5.5385 | 4.6154 | 3.6923 | 2.7692 | 1.8462 | 0.92308 | -2.8866e-15
Optimal Trend | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9
Hours per day | 2020-09-05: 0.92308
Use Cases | 2020-09-05: Time Estimate; 2020-09-06: Sprint Assigned; 2020-09-07: Status
See map broken up by DEC regions | 2020-09-05: 3; 2020-09-06: 1; 2020-09-07: Done
Create store to spend money in | 2020-09-05: 3; 2020-09-06: 1; 2020-09-07: In Progress
Create a start screen | 2020-09-05: 3; 2020-09-06: 1; 2020-09-07: In Progress
Create an end screen | 2020-09-05: 3; 2020-09-06: 1; 2020-09-07: In Progress