## Product Backlog
Use Cases | Time Estimate
Save Game | 6
Create difficulty options | 5
Create color blind settings in options | 4
Create volume settings in options | 3
Have realistic options in the store to slow the spread | 5
Create a tutorial | 6
Regions change color based on infection | 4
Insects spread between regions | 2
35

## Sprint 1
| 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18
Optimal Trend | 12 | 11.0769 | 10.1538 | 9.2308 | 8.3077 | 7.3846 | 6.4615 | 5.5385 | 4.6154 | 3.6923 | 2.7692 | 1.8462 | 0.92308 | -2.8866e-15
Actual Trend | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 7 | 3 | 0
Hours per day | 2020-09-05: 0.92308
Use Cases | 2020-09-05: Time Estimate; 2020-09-06: Status
See map broken up by DEC regions | 2020-09-05: 3; 2020-09-06: Done
Create store to spend money in | 2020-09-05: 3; 2020-09-06: Done
Create a start screen | 2020-09-05: 3; 2020-09-06: Done
Create an end screen | 2020-09-05: 3; 2020-09-06: Done

## Sprint 2
| 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02
Optimal Trend | 12 | 11.0769 | 10.1538 | 9.2308 | 8.3077 | 7.3846 | 6.4615 | 5.5385 | 4.6154 | 3.6923 | 2.7692 | 1.8462 | 0.92308 | -2.8866e-15
Actual Trend | 11 | 11 | 11 | 11 | 10 | 10 | 8 | 8 | 6 | 6 | 4 | 4 | 1
Hours per day | 2020-09-19: 0.92308
Use Cases | 2020-09-19: Estimate; 2020-09-20: Status
Insects spread at a reasonable rate | 2020-09-19: 4; 2020-09-20: In progress
Each region is clickable to show infection and statistics | 2020-09-19: 8; 2020-09-20: Done